## Slide 1
KAILA
Right-Path Startup Guide
A practical guide for starting the first KAILA pilot the right way.
Validation first. Provider supply first. Trust first. Software second.
Based on the KAILA Founder-Grade Package
KAILA Right-Path Startup Guide
01

## Slide 2
The Main Rule
KAILA starts as a validation project before it becomes a software project.
The browser MVP and native wrapper already exist.
Build proof next.
Risky path
App without users -> weak evidence
Right path
App-led concierge pilot -> evidence -> focused improvements
First proof needed: requests, provider offers, completed/strongly matched jobs, ratings, and manageable disputes.
KAILA Right-Path Startup Guide
02

## Slide 3
90-Day Starting Roadmap
A disciplined sequence for turning KAILA into evidence.
Days 1-7
Foundation
Days 8-21
Recruit providers
Days 22-30
Validate clients
Days 31-75
Concierge pilot
Days 76-90
Review decision
Output: forms, sheets, provider rules, provider list, real requests, tracked offers, ratings, and go/no-go decision.
KAILA Right-Path Startup Guide
03

## Slide 4
Phase 0: Founder Alignment
Agree on the operating philosophy before asking anyone to join.
KAILA is not just an app.
It is a local trust and service-matching system.
Local first
Provider first
Trust first
Manual first
Free first
Start in one focused place, not everywhere.
Build supply before client demand.
Use trust levels instead of pretending all providers are equal.
Prove the workflow manually before building the product.
KAILA Right-Path Startup Guide
04

## Slide 5
Phase 1: Define the First Pilot
Keep the first version narrow enough to operate and measure.
Area
Gingoog City or selected barangay cluster
Clients
Households, renters, homeowners, students, small businesses
Providers
Skilled workers, technicians, freelancers, shops
Duration
30-45 days of active matching
Pricing
Free pilot for clients and providers
Goal: learn fast without creating a heavy operation.
KAILA Right-Path Startup Guide
05

## Slide 6
Choose 5-8 Starting Categories
Select practical, common, and manageable local services.
Appliance repair
urgent household need
Plumbing
leaks and clogs
Electrical
common but safety-sensitive
Computer repair
students/offices/homes
Motorcycle repair
local mobility need
Carpentry / maintenance
small repairs
Cleaning / odd jobs
flexible supply
Digital services
layouts, designs, basic tech
Avoid high-risk or hard-to-control services at the start.
KAILA Right-Path Startup Guide
06

## Slide 7
Phase 2: Build the Manual System
Use the existing app first. Let the concierge pilot teach the next improvements.
Facebook Page
public presence
In-app provider interview
supply intake
In-app client survey/request
demand intake
Provider Sheet
supply database
Request Tracker
job evidence
Messenger
manual matching
This is the concierge pilot: manually doing what the app will later automate.
KAILA Right-Path Startup Guide
07

## Slide 8
Phase 3: Recruit Providers First
Clients will only trust KAILA if relevant providers are already available.
50
target providers
5-8
categories
3-5
providers per request
Recruitment channels
Personal network and local contacts
Facebook groups, Marketplace, service posts
Repair shops, hardware stores, motorcycle shops
Community referrals and provider-to-provider referrals
Provider pitch must answer:
Will this help me get clients?
Is it free?
Can I accept or decline?
Can I control my price?
KAILA Right-Path Startup Guide
08

## Slide 9
Phase 4: Make Trust Visible
Do not present all providers as equally verified.
1
Listed
2
Identity Verified
3
Work Verified
4
Top Rated
5
Certified / Business Verified
Trust grows through identity checks, work samples, completed pilot jobs, ratings, response speed, and low dispute rate.
KAILA Right-Path Startup Guide
09

## Slide 10
Phase 5: Validate Client Demand
Listen for repeated pain points before launching publicly.
Lisod mangita ug kasaligan
trust problem
Walay klaro nga presyo
pricing problem
Dugay mu-reply
response problem
Referral ra gyud mi magsalig
informal discovery
Wala ko kabalo kinsa duol
location discovery
Target: 100 resident responses, or at least 30-50 strong responses before starting the first requests.
KAILA Right-Path Startup Guide
10

## Slide 11
Phase 6: Run the Concierge Pilot
The first KAILA workflow should be manual, measurable, and repeatable.
Client request
KAILA checks details
Forward to providers
Offers received
Client chooses
Job + ratings
Record every step: time received, providers contacted, response time, offers, selected provider, agreed amount, completion, ratings, and issues.
KAILA Right-Path Startup Guide
11

## Slide 12
Practical Matching Script
Use a consistent request format so providers can respond quickly.
KAILA Request #001
Category: Plumbing
Area: Barangay 23, Gingoog City
Problem: Clogged kitchen sink
Urgency: Today
Budget: PHP 500-PHP 800
Can you take this job? If yes, send your offer and available time.
Send to 3-5 matching providers.
Record who replies and how fast.
Let the client compare offers clearly.
Do not share unnecessary private details too early.
KAILA Right-Path Startup Guide
12

## Slide 13
Phase 7: Track the Right Metrics
The pilot must be judged by evidence, not excitement.
Active providers
supply strength
Requests
demand
Response rate
provider seriousness
Offers/request
market activity
Completed jobs
actual value
Ratings
trust
Disputes
risk
GMV
peso value
GMV = total peso value of completed jobs through KAILA.
KAILA Right-Path Startup Guide
13

## Slide 14
Phase 8: Go / No-Go Decision
After the pilot, choose the next move based on evidence.
Proceed to MVP
Real requests, provider response, 15+ completed/strongly matched jobs, ratings accepted, disputes manageable.
Narrow scope
Only 1-2 categories work strongly. Focus on the winning categories instead of stopping.
Redesign / pause
Providers refuse, clients avoid posting, trust barriers are too high, or operations cannot support matching.
Decision question: What does the data say?
KAILA Right-Path Startup Guide
14

## Slide 15
Phase 9: Build MVP Only After Strong Signals
The MVP should digitize the proven manual workflow.
Client
Register
Post request
Compare offers
Choose provider
Confirm + rate
Provider
Create profile
View matching requests
Send offer
Update job
Rate client
Admin
Manage users
Verify providers
Track jobs
Handle disputes
View reports
KAILA Right-Path Startup Guide
15

## Slide 16
Do Not Build These Yet
Avoid heavy features before the core marketplace behavior is proven.
In-app payments
GPS live tracking
Native app polish beyond the current wrapper
Complex AI matching
Large-scale automation
First prove:
request posting -> provider offers -> client selection -> job completion -> ratings -> trust improvement
KAILA Right-Path Startup Guide
16

## Slide 17
Phase 10: Monetize Slowly
Do not charge until providers feel real value.
1
Free pilot
build trust
2
Visibility products
premium profiles /
featured listing
3
Lead or transaction revenue
lead credits / subscriptions / commission
Recommended first paid product: Provider visibility, not commission.
KAILA Right-Path Startup Guide
17

## Slide 18
Founder Roles Must Be Clear
Even if one person holds multiple roles, responsibilities should be named.
Product / Tech
Provider Acquisition
Operations
Marketing / Community
Finance / Admin
Business Strategy
KAILA
Pilot Team
KAILA Right-Path Startup Guide
18

## Slide 19
Protect KAILA Early
Treat data, brand, provider records, and internal strategy carefully.
Provider list
limit access
Client requests
share only needed details
Photos/videos
ask permission before posting
Ratings/disputes
keep factual records
Brand/docs
organize source files
Code
clarify ownership
Trust can be damaged by poor data handling before the app even exists.
KAILA Right-Path Startup Guide
19

## Slide 20
Weekly Operating Rhythm
Review evidence, improve the workflow, and assign next actions.
Providers joined
Active providers
Client requests
Top categories
Response time
Offers/request
Completed jobs
Ratings
Disputes
Next actions
Weekly output: metrics summary, top lessons, problems found, assigned next actions, and decision notes.
KAILA Right-Path Startup Guide
20

## Slide 21
First 7 Days: Exact Starter Checklist
Start immediately without building the app.
Day 1
Pilot scope
Day 2
Facebook page
Day 3
Provider form + sheet
Day 4
Client form + tracker
Day 5
Rules + scripts
Day 6
100 provider leads
Day 7
Start outreach
Week 1 is successful if KAILA can be explained clearly, collect signups, receive requests, and track everything.
KAILA Right-Path Startup Guide
21

## Slide 22
Recommended First Move
KAILA Gingoog Concierge Pilot
50
providers
100
client responses
30
real requests
15
completed/strongly matched jobs
5-8
categories
30-45
active matching days
If the pilot shows strong behavior and trust, build the MVP around the proven workflow.
KAILA Right-Path Startup Guide
22